# Cedar Ridge Tournament 2026 - Prep Day Planning Brief

# Document Information

Document: Tournament Prep Brief

Status: CURRENT - ACTIVE

Prepared by: Tom Iverson, Head Instructor

Date: January 1, 2027

Distribution: Aaron Delgado, Raj Patel, Maya Chen

# 1. Tournament Schedule

The Cedar Ridge Annual Fall Tournament 2026 is confirmed for January 17, 2027. Prep day activities will begin January 14 with final setup on January 16.

January 10: Equipment audit deadline (assigned to Aaron)

January 12: Referee scheduling finalized

January 14: Venue prep begins

January 15: Photography and media setup

January 16: Final walkthrough and equipment staging

January 17: Tournament day

# 2. Equipment Audit Assignment

Assigned to: Aaron Delgado

Deadline: January 10, 2027

Aaron is responsible for conducting a complete equipment audit before the tournament. This includes:

Physical count of all adult and youth equipment

Visual inspection for damage or wear

Cross-reference with Airtable Equipment Tracker

Photo documentation of storage room condition

Update Monday board with audit status and findings

Submit purchase request for any shortfall items

Raj Patel reported on December 28 that he identified and removed 2 damaged adult kote pairs from active inventory. Aaron should verify this during the audit and confirm Airtable records have been updated.

# 3. Venue and Logistics

The main dojo will be reconfigured for tournament layout. Tom will coordinate with the landlord for extended hours access January 14-17.

Court setup: 3 competition courts (tape lines, judge positions)

Spectator seating: Folding chairs along north wall (capacity ~80)

Registration table: Near main entrance

Medical station: Back hallway near restrooms

Equipment staging: Storage Room B (adjacent to courts)

# 4. Student Registration Status

Registration is currently in progress on the Monday board. As of January 1:

Adult division: 12 registered (target: 16-20)

Youth division: 8 registered (target: 12-16)

Registration deadline: January 12, 2027

Late registration: Accepted until January 15 with $10 late fee

# 5. Budget Summary

Tournament budget was approved on December 20. Key line items:

Venue prep supplies: $200 (approved)

Equipment replacement: TBD pending audit results

Trophies and awards: $350 (ordered from Portland Engraving)

Photography: $150 (volunteer Maya Chen)

Miscellaneous: $100 reserve

Note: Any equipment purchases at or above $175 require co-owner approval per Cedar Ridge financial policy.

# 6. Communication Plan

Tom will send weekly updates to the team via email

Monday board is the primary task tracker for all prep activities

Aaron to draft and send participant communication by January 12

Raj will coordinate equipment staging on January 16